# Development Plan — Web-first → Native, €200/mo Pre‑Revenue (v1)

## 0) Constraints and intent

- Solo founder. One city. Web app first. Native app as soon as viable.

- Budget until revenue: €200/month all‑in. Reinvest 100% of profit into hiring and native build.

- Core loop and scoring: per Functional Spec — App Flow & Pricing (v3). This plan focuses on execution.

## 1) Objectives and success gates

Product

- Median time‑to‑confirm ≤ 24h, median TTD ≤ 7 days.

- Conversion: match→proposal ≥ 40%, proposal→confirm ≥ 55%, confirm→show ≥ 80%.

Monetisation (web)

- Payer share ≥ 6% MAU by week 8 of public beta.

- ARPPU ≥ €12/month web‑only (subs + credits).

Ops/Safety

- Verification pass‑rate ≥ 70% of active users (phased; see costs).

- Moderation SLA ≤ 24h (manual at start).

Go‑native trigger (start RN build ASAP once met for 14 days)

- MAU ≥ 1,000 and confirmed dates/WAU ≥ 0.15 or daily reminder reach < 35% due to lack of push.

- EBITDA ≥ €2k/month (post tools and founder salary if any; pre‑revenue this is 0).

## 2) Budget guardrails (€200/mo pre‑revenue)

Must‑haves (target ≤ €150/mo):

- Hosting: Vercel Hobby (free) → upgrade when needed.

- DB/Auth/Realtime/Storage: Supabase Pro Small ~€25/mo (or free tier until crossed).

- Email: Postmark €15/mo (10k emails). Alternative: SES ~€0.10/1k + minimal infra.

- SMS: MessageBird/Twilio pay‑as‑you‑go. Cap €20/mo.

- Analytics: PostHog Cloud Free or Amplitude Free (10M events/mo free).

- Monitoring/Errors: Sentry Free.

- Moderation: start with manual review + basic URL/image rules (cost €0). Add provider later.

- Domain + privacy: €2/mo (annual domain ~€20). CDN included with Vercel.

Nice‑to‑adds at revenue:

- Video liveness (Persona/Onfido): budget €2–3/verification. Start with photo verification + selfie pose until revenue.

- Image moderation API: €25–75/mo later.

Cap runtime at €200 until revenue. Defer paid experiments and SMS where possible.

## 3) Architecture (lean)

- Frontend: Next.js (App Router) + React + TypeScript + Tailwind. Mobile‑first. PWA optional later.

- Backend: Supabase (Postgres + Auth + RLS + Realtime + Storage + pg_cron + Edge Functions).

- Payments: Stripe Checkout + Webhooks (subs + credits).

- Email/SMS: Postmark + MessageBird/Twilio (fallback only). ICS attachments via server.

- Analytics/Flags: PostHog + simple env flags (flip to GrowthBook after revenue).

- Moderation: manual queue, blocklists, rate limits. Add API later.

- Observability: Sentry; simple health pings; DB logs.

## 4) MVP scope freeze (web)

- Onboarding with email; optional phone. Age gate. Photo + selfie pose check (no liveness SDK yet).

- Profile with prompts, photos, “I’m usually free…” availability and lead‑time.

- Discovery feed + like; match.

- Propose 2–3 times; receiver Confirm or None suits → 2–3 times.

- Reminders email‑first; ICS calendar add.

- Chat unlocks only after confirm.

- Post‑date 15s survey → scores.

- Expired→Reopen (receiver‑paid) with credits.

- Pricing: Momentum+ + Credits (per Functional Spec).

- Safety: block/report; manual moderation queue; visible SLA timer text.

Out of MVP (defer): native push, voice intros, low‑anxiety mode, heavy moderation API, maps/venues.

## 5) Build plan (solo) — weeks 1–8

Week 1 — Project + Auth + Data

- Repo, CI (Vercel). Supabase project. RLS baseline.

- Tables: users, profiles, likes, matches, messages, proposals, confirmations, closes, surveys, scores_daily, entitlements, transactions, reports.

- File upload to Storage with signed URLs. Basic photo checks.

Week 2 — Profiles + Feed + Like/Match

- Profile CRUD, prompts, photos, availability bands.

- Feed endpoint + basic rank using Action Speed baseline + Profile Quality prior.

- Like/match flows. Event logging to PostHog.

Week 3 — Propose/Confirm/None‑suits

- Proposal sheet (2–3 slots). Confirm, None suits → 2–3.

- Expiry in 72h; proposal reminders at 24/48h.

- ICS generator. Timezone handling.

Week 4 — Messaging + Reminders

- Realtime chat on confirm. Pre‑date reminders T‑24/T‑2.

- Manual report/block + moderation queue UI.

Week 5 — Scoring + Pricing

- Implement Action Speed engine (likes/day, first‑action bonuses, turn‑based penalties as per spec). Inactivity floor 50.

- Implement Profile Quality MAR and Reliability events.

- Stripe Checkout: Momentum+ + credits; entitlements; receipts.

Week 6 — Safety + Compliance + SEO

- TOS/Privacy, consent, deletion/export endpoints.

- Report SLA clock UI. Basic CSAM/URL keyword filters.

- Landing page + waitlist + city gating.

Week 7 — QA + Load + Beta Setup

- Playwright E2E: signup→match→propose→confirm→chat→survey→reopen.

- k6 load for feed and messaging.

- Seed closed beta cohort (balanced by gender/age). Creator tracking links.

Week 8 — Closed Beta → Public Waitlist

- Run a city‑limited beta (100–300 users). Fix criticals. Measure funnels.

- Open public waitlist while keeping city gating.

## 6) Post‑MVP roadmap (weeks 9–16)

- Week 9–10: payment polish, refunds, downgrade flow, credit ledger export; spam heuristics.

- Week 11–12: availability‑driven smart suggestions; transparency “why this match”.

- Week 13–14: verification upgrade (add liveness if revenue allows). Image moderation API.

- Week 15–16: referral programme, creator dashboards, outcome learning v1.

## 7) Reinvestment and hiring ("as soon as possible")

Policy: 100% EBITDA → product, growth, trust & safety. Keep buffer ≥ one month of fixed burn.

Earliest hires (contract → FTE), start when monthly revenue ≥ €1,500 and funnels healthy:

- Part‑time Moderator (10 h/wk). €400–600/mo. Frees founder time.

- Freelance Brand/UGC Editor (10 h/wk). €400–600/mo. Improves asset quality.

Native app push — hire ASAP once any one is true:

- Monthly net revenue ≥ €4k, or

- MAU ≥ 1,000 with confirm‑to‑show ≥ 75% and email reminder reach < 40%, or

- Creator demand requires store presence.

Role: React Native Engineer (contract 8–10 weeks)

- Scope: RN app (Expo), auth, profiles, feed, propose/confirm, chat, push, IAP parity, deletion.

- Cost: €8–12k total contract. Fund via reinvested profit.

Then: Product Designer (T‑shaped), Backend/Data contractor. Sequence hires as revenue allows; never drop below 1‑month buffer.

## 8) Native app plan (parallel, ASAP once funded)

- Week 0: set up monorepo. Shared types and business logic. API unchanged.

- Week 1–2: RN shell, auth/profile/feed/match.

- Week 3–4: propose/confirm/none‑suits, chat, push (FCM/APNS), background reminders.

- Week 5–6: IAP (Apple/Google), entitlements sync, verification SDK, block/report.

- Week 7–8: QA, crash reporting, ASO assets, legal (delete in‑app), staged rollout.

## 9) Security, privacy, compliance (lean)

- RLS on all tables; owner/match scoping.

- PII encryption at rest. Signed URLs. 2FA on admin.

- GDPR: consent log; DSAR export/delete; data retention policy (delete 30d after account deletion).

- Payments: clear auto‑renew terms; web cancel; receipts.

## 10) Observability and KPIs

- Tech: p95 API < 300 ms; message RTT < 500 ms; uptime ≥ 99.5%.

- Funnel: match→proposal, proposal→confirm (≤24h), confirm→show, median TTD.

- Marketplace: verification %, ghost‑rate, report rate, moderation SLA.

- Revenue: payer share, ARPPU, credits share, refunds.

Dashboards in PostHog. Daily email digests. Alerts on 5xx spikes and job failures.

## 11) Growth on €200/mo

- Zero‑paid ads. Use:

  - Creator partnerships on rev‑share or CPA‑per‑confirmed‑date.

  - Referral credits on shows.

  - Waitlist with city pick; email drips to convert.

- Content: one landing, three SEO pages (“meet faster”, “how it works”, city page). Use free tools.

- Street teams and micro‑events later once revenue exists.

## 12) Risk controls

- Cold start: city‑only, invite cohorts, seed both sides evenly.

- Inaction: strict proposal expiry, harsh turn penalties, reopen paid.

- Spam/safety: manual mod + block lists; throttle velocity; verification upgrade at revenue.

- Cost creep: SMS caps; image compression; verification only at confirm stage in beta.

## 13) Checklists

Pre‑launch: RLS tests, consent text, email templates, ICS validation, refund logic, DSAR endpoints, mod queue macros.

Launch week: seed cohort, monitor funnels hourly, fix top 5 issues only, publish status page.

Post‑launch weekly: Mon funnel + reliability review; Wed experiment readouts; Fri cash snapshot + reinvestment decisions.

## 14) Cut‑line if over budget

- Drop SMS; email only.

- Switch Postmark→SES.

- Defer paid verification; keep selfie pose + manual check.

- Pause paid creators; referral only.

## 15) What to do today

- Create Supabase project and tables; set RLS.

- Scaffold Next.js app; profile + availability.

- Implement propose/confirm/none‑suits; 72h expiry; reminders.

- Add Stripe Checkout for credits + Momentum+.

- Ship closed beta to 50–100 users in one city.