# Marketing Plan — Web‑first Launch, €200/mo Pre‑Revenue → Native (v1)

## 1) Objectives and north‑star

- North‑star: confirmed dates/WAU ≥ 0.15 and median TTD ≤ 7 days.

- Acquisition: CAC‑to‑confirmed‑date ≤ €25 in paid tests; organic first.

- Monetisation: payer share ≥ 6% MAU by Week 8 of public beta; ARPPU ≥ €12.

- Supply balance: female confirm‑in‑24h ≥ 35% for 14 days before scaling male acquisition.

- Trust: verification ≥ 70% of active users by Month 2; moderation SLA ≤ 24h.

## 2) Positioning and message

- Promise: Spend less time texting. Meet faster.

- Why believe: structured proposals, 72h expiry, receiver‑paid reopen, speed scoring, reliability.

- Taglines:

  - "Meet in days, not months."

  - "Propose two times, get one confirmed."

  - "Real dates > infinite chats."

- Proof assets: live counters (city TTD median), anonymised success stories, transparent safety SLA timer screenshots.

- Voice: clear, direct, non‑sappy. No romance clichés. Outcome‑driven.

## 3) Ideal customer profiles (ICP) and first city rollout

- City 1: Dublin (Leinster). One‑city gating until funnels stable.

- ICP‑A (women 22–32): safety‑first, low patience for chat. Channels: TikTok/IG Reels, creator UGC, WhatsApp circles.

- ICP‑B (men 24–34): time‑constrained professionals. Channels: TikTok/IG, Reddit subs (r/ireland, r/dating_advice within rules), LinkedIn founder content.

## 4) Funnel architecture (AARRR)

- Awareness: TikTok/IG UGC, founder content, micro‑PR, Reddit organic, referral stories.

- Acquisition: waitlist landing (city gate), QR codes, creator links, referral links.

- Activation: verification + availability + first 8 likes within 48h → Speed=100.

- Retention: reminders, reopen mechanic, outcome credits, Momentum+ trial for under‑supplied cohorts.

- Referral: credits or Momentum+ month when both mark “went.”

## 5) Low‑budget channel plan (≤€200/mo pre‑revenue)

Primary (cost ≈ time):

- UGC engine (TikTok/IG Reels) — 3–5 short videos/week.

  - Formats: Proposal in 20s, Texting vs Proposals, 72h expiry explained, Date confirmed in 30s, Women’s inbox triage.

  - CTA: “Dublin only. Meet faster.”

- Founder‑led LinkedIn/Twitter — build in public weekly: metrics, learnings, transparency on safety.

- Reddit participation — authentic comments, no spam; link to a neutral explainer page.

- Referral on shows — post‑date screen makes share easy; credits unlock Fast Pass/slots.

Secondary (light €):
 5) Creator rev‑share tests — 2–3 micro‑creators (3–15k followers). Compensation €5 per confirmed date capped at €50/creator/mo pre‑revenue.
 6) Campus/office ambassadors (unpaid perks) — codes earn credits; monthly leaderboard inside app.
 7) Flyer/QR in cafes/gyms (printing €20–40 once). Minimal copy, trust cues.

## 6) Creators & ambassadors (CPA‑per‑confirmed‑date)

- Offer: €5 per confirmed date (both verified, confirmed within 7 days of sign‑up via the creator link). Hard cap per creator per month in pre‑rev.

- Tracking: unique referral code + UTM + in‑app attribution. Dashboard: installs, verifications, confirms, CPA‑date.

- Brief: 3 hooks

  - “Two time windows. One tap confirm. Done.”

  - “Stop texting strangers for weeks.”

  - “Dates confirmed in 24h challenge.”

- Disclosure: #ad, ASA compliance. Provide caption kit and B‑roll of the flow.

## 7) Referral program (outcome‑linked)

- Trigger: award when both mark “went.”

- Reward: referrer +40 credits; referee +20 credits; double for under‑supplied cohort during seeding.

- Fraud controls: both verified; device/IP checks; 30‑day lock before credit cash use on reopens/slots.

- Loops: in‑app share cards after confirm and after show; email prompt next morning.

## 8) Lifecycle messaging map

Channels: email primary, SMS fallback, in‑app banners.

- D0 Welcome: verify + availability + 8 likes in 48h → Speed 100. Subject: “Ready to meet this week?”

- D1 Nudge: “Propose 2–3 times to your top match.”

- Proposal sent (24/48h): to receiver: “Pick one or send 2–3.”

- Confirmed (T‑24/T‑2): reminders + ICS.

- Expired: sender sees “Expired.”; receiver sees “Reopen & propose 2–3 times.”

- Post‑date: survey + referral share + credits recap.

- Dormant 7d: “Your Speed holds at 50. Send 4 likes today to re‑enter discovery.”

## 9) Content system (3 months)

- Pillars:

  - Meet faster education (how the flow works).

  - Safety & respect (SLA, reliability, anti‑ghosting).

  - Social proof (anonymised wins, median TTD in Dublin).

- Cadence: 3–5 Reels/TikToks/week; 1 LinkedIn founder post/week; 1 blog post/fortnight (SEO: “first date Dublin”, “how to ask for dates fast”, “72‑hour rule dating”).

- Templates: subtitle style, hook in 1s, on‑screen steps, CTA.

## 10) Landing + SEO

- Pages: Home, How it Works, Safety, Pricing, Dublin hub (“date ideas”, “best coffee for first date”), Explainer blog.

- CTAs: city gate → email capture → app.

- Schema: FAQ, HowTo for proposal flow, LocalBusiness for city page.

- Lead magnets: “20 one‑line proposals that work.”

## 11) Measurement and experimentation

- Event taxonomy: page_view, signup_started, verified, availability_set, like_sent, match, proposal_sent, confirm, none_suits, reopen, expired, show_marked, referral_share, purchase.

- Dashboards: AARRR, proposal→confirm ≤24h, confirm→show, reopen→confirm, credits usage, payer share.

- Cadence: weekly experiment slate (max 2). 7‑day reads. Stop if no signal.

- Sample tests:

  - Hook video A/B (flow vs social proof).

  - Referral copy: credits vs Momentum+ month.

  - Creator CPA caps €30 vs €50.

  - Women’s 2× credit window on shows (on/off).

## 12) Budgeting and scale rules

- Pre‑rev €200/mo cap: email + domain + minimal SMS + one‑off print + creator CPA tests (tiny caps).

- Reinvest rule: once net revenue > €0, push 30% of EBITDA into growth weekly until CAC‑date ≤ €25 is saturated.

- Scale gates: spend ↑ only if week’s CAC‑date ≤ target and retention ≥ target (payer share ≥ 6%, show‑rate ≥ 75%).

## 13) City seeding playbook (Dublin)

- Phase 0 (2 weeks): 150–300 waitlist via UGC + creator microtests. Verify ≥70%.

- Phase 1 (2–4 weeks): closed beta 100–300, balance cohorts. Track confirm ≤24h.

- Phase 2: open to waitlist; cap new male sign‑ups if female confirm‑in‑24h falls <35% for 7 days; increase women creator budget.

## 14) Community without offline ops

- Interest hubs: coffee, walks, climbing, board games; in‑app only; weekly prompts.

- Discord optional: rules: no meetups arranged by us; peer‑led only; link back to proposals.

- UGC prompts: “Drop two times you’re free this week.”

## 15) Legal and claims

- No deterministic claims (“will get a date”). Use city medians and confidence intervals. Disclose paid creator content. Clear terms on credits and non‑refundability of reopens. GDPR‑compliant email/SMS consent.

## 16) Risk and mitigations

- Receiver overload: inbound governor; queue; women‑first credits.

- Spam optics: caps and structured proposals; no pay‑to‑spray.

- Scam/bot: verification at confirm; manual mod until API.

- PR backlash: publish safety policy and enforcement transparency; fast takedowns.

## 17) Timeline

- Week 0: landing + waitlist + UGC cadence start.

- Week 1–2: creator outreach; first three creator posts; referral set live.

- Week 3–4: closed beta launch; social proof content from real confirms.

- Week 5–8: open to waitlist; double down on winning creators; small paid tests if revenue.

- Month 3: prepare native announcement funnel.

## 18) Asset checklist

- Logo/wordmark; color tokens; Reel/TikTok templates; landing hero, safety visuals; step cards of proposal/confirm; referral share cards; creator brief; one‑pager for partners; status page screenshot; FAQ.

## 19) Scripts and creative briefs

- UGC hook lines:

  - “Dating apps are slow. This one makes you propose two times.”

  - “The 72‑hour rule that ends ghosting.”

  - “We got a date confirmed in 37 seconds.”

- Explainer video beats (30–45s): problem → our loop → confirm in‑app → calendar pop → post‑date survey → credits → CTA.

## 20) KPIs and weekly review

- Acquisition: installs, verifies, CAC‑date.

- Activation: matches, proposal rate, confirm ≤24h.

- Retention: weekly active, shows, payer share.

- Monetisation: ARPPU, credits spend split, refunds.

- WOM: referral rate/post‑date, K‑factor.

## 21) Scale beyond Dublin (later)

- Clone the playbook in city 2 after 4 weeks of target metrics. Localise content, creators, and SEO hubs. Maintain city gating until each market shows healthy funnels.